FUNCTIONAL SPECIFICATION DOCUMENT

Mining Contractor Management System (MCMS)

| Document Version | 1.0 |
| --- | --- |
| Document Status | Draft |
| Business Area | Mining Operation – Coal Mining |
| System Type | Web-Based Mining Contractor Management System |
| Prepared For | Coal Mining Company |
| Date | August 2026 |

# 1. DOCUMENT PURPOSE

Dokumen ini mendefinisikan kebutuhan fungsional untuk Mining Contractor Management System (MCMS), yaitu sistem terintegrasi untuk mengelola aktivitas penambangan yang dilaksanakan oleh mining contractor.

Sistem dirancang untuk memberikan kontrol kepada Owner atas:

Mining plan dan target produksi

Aktivitas dan progress kontraktor

Fleet dan equipment

Manpower

Coal dan overburden production

Hauling

Survey dan quantity measurement

Fuel consumption

Contractor performance

Contract utilization

SLA/KPI

Penalty dan incentive

Progress claim

Billing verification

Cost per unit

Management reporting

Tujuan akhirnya adalah membentuk single source of truth antara Owner, Mining Operation, Engineering, Survey, Finance, Procurement/Commercial, dan Contractor.

# 2. BUSINESS OBJECTIVES

Production Control: Actual production dapat dibandingkan dengan target secara harian.

Contractor Control: Performance setiap contractor dapat dimonitor.

Quantity Assurance: Quantity invoice harus berdasarkan quantity yang telah diverifikasi.

Cost Control: Mining cost dapat dimonitor sampai level contractor/pit/activity.

Contract Control: Nilai kontrak, utilization, dan remaining contract dapat dimonitor.

Equipment Control: Productivity dan utilization equipment dapat dianalisis.

Fuel Control: Fuel consumption dapat dibandingkan dengan production output.

Operational Visibility: Management mendapatkan informasi operasional secara near real-time.

Billing Accuracy: Mengurangi dispute dan overbilling contractor.

Performance Management: KPI, penalty, incentive, dan SLA dihitung secara sistematis.

Auditability: Seluruh transaksi memiliki approval dan audit trail.

# 3. SYSTEM SCOPE

MCMS mencakup proses Contract → Planning → Operation → Measurement → Reconciliation → Performance → Billing → Cost → Management Insight.

Functional domain:

Master Data Management

Contractor & Contract Management

Mining Planning

Daily Operation

Equipment & Fleet Management

Coal Production

Overburden Management

Hauling Management

Survey & Measurement

Fuel Management

Contractor Performance Management

Contract Progress & Utilization

Progress Claim

Billing Verification

Penalty & Incentive

Cost Management

HSE Performance

Dashboard & Analytics

Workflow & Approval

Document Management

Integration

Audit Trail & Security

# 4. HIGH-LEVEL BUSINESS PROCESS

CONTRACT & WORK ORDER

↓

MINING PLAN

↓

MONTHLY / WEEKLY / DAILY TARGET

↓

CONTRACTOR RESOURCE PLAN

↓

EQUIPMENT + MANPOWER

↓

DAILY MINING OPERATION

↓

OB Removal / Coal Getting / Coal Hauling / Road & Supporting Activities

↓

SURVEY / MEASUREMENT

↓

PRODUCTION RECONCILIATION

↓

CONTRACTOR PERFORMANCE

↓

QUANTITY VERIFICATION

↓

PROGRESS CLAIM

↓

COMMERCIAL VERIFICATION

↓

PENALTY / INCENTIVE

↓

BILLING

↓

COST ANALYSIS

↓

MANAGEMENT DASHBOARD

# 5. USER & ROLE MANAGEMENT

Roles: System Administrator, Mining Operation, Mine Engineering, Surveyor, Dispatch, Fuel Controller, HSE, Contractor User, Contractor Supervisor, Owner Supervisor, Commercial, Procurement, Finance, Mine Manager, General Manager, Director, Auditor.

Access control harus mendukung Role-Based Access Control, menu-level authorization, function-level authorization, site-level access, contractor-level access, approval authorization, data confidentiality, serta Read/Create/Update/Approve/Cancel privileges.

Contractor hanya dapat mengakses data yang terkait dengan perusahaan/kontraknya sendiri.

# 6. MASTER DATA MANAGEMENT

Organization: Company, Site, Mining Area, Pit, Block, Seam, Stockpile, Disposal, Hauling Route, Workshop, Fuel Station.

Contractor Master: Contractor ID, Contractor Name, Vendor ID, Address, Contact Person, Contract Number, Contract Start, Contract End, Status, Operational Area, PIC Owner, PIC Contractor.

Equipment Master: Equipment ID, Contractor, Equipment Category, Equipment Type, Brand, Model, Serial Number, Capacity, Ownership, Commission Date, Status.

Equipment Category: Excavator, Dump Truck, Dozer, Grader, Compactor, Water Truck, Fuel Truck, Loader, Support Equipment.

Activity Master: OB Removal, Topsoil Removal, Coal Getting, Coal Hauling, OB Hauling, Road Maintenance, Dewatering, Land Clearing, Rehabilitation, Supporting Work.

# 7. CONTRACT MANAGEMENT

Contract Header: Contract Number, Contractor, Contract Type, Effective Date, Expiry Date, Contract Value, Currency, Site, Scope of Work, Contract Owner, Payment Terms, Retention, Status.

Contract Rate dapat memiliki multiple rate berdasarkan Activity, Unit, Effective Date, Distance Range, Material, Equipment, Location, Escalation Formula, Fuel Adjustment, Minimum Quantity, dan Maximum Quantity.

Contoh rate: OB Removal (Rp/BCM), Coal Getting (Rp/Ton), Coal Hauling (Rp/Ton-KM), Equipment Rental (Rp/Hour), Road Maintenance (Rp/Month).

Contract Amendment harus mendukung rate revision, contract extension, scope addition/reduction, dan contract value adjustment. Semua perubahan harus mempertahankan historical version.

# 8. MINING PLAN

Planning hierarchy: Life of Mine → Annual Plan → Monthly Plan → Weekly Plan → Daily Plan.

Production Target dapat didefinisikan berdasarkan Site, Pit, Contractor, Activity, Material, dan Period.

KPI: OB Target, Coal Target, Stripping Ratio, Hauling Target, Equipment Productivity, Fuel Ratio.

# 9. DAILY OPERATION

Contractor melakukan input Daily Production Report.

Informasi minimum: Date, Shift, Contractor, Pit, Block, Activity, Material, Loading Point, Dumping Point, Equipment, Quantity, Distance, Working Hour, Standby Hour, Breakdown Hour.

Workflow: Contractor Input → Contractor Supervisor → Owner Supervisor → Verified Production.

Setelah verified, data menjadi dasar reconciliation.

# 10. EQUIPMENT & FLEET MANAGEMENT

Equipment Status: Working, Standby, Breakdown, Maintenance, Waiting, Idle.

Equipment Hours: Available Hours, Working Hours, Standby Hours, Breakdown Hours, Maintenance Hours.

KPI:

Physical Availability (PA) = Available Hours / Scheduled Hours × 100%

Utilization (UA) = Working Hours / Available Hours × 100%

Excavator Productivity = BCM / Working Hour

Hauling Productivity = Ton / Truck Hour

# 11. OVERBURDEN MANAGEMENT

System mencatat Pit, Block, Loading Point, Disposal, Equipment, Contractor, Distance, BCM, dan Working Hour.

Dashboard: OB Plan, OB Actual, Achievement %, BCM/hour, BCM/equipment, Cost/BCM, Contractor ranking.

# 12. COAL PRODUCTION

Coal production flow: Coal Getting → ROM → Coal Hauling → Stockpile → Crusher / Processing.

Data: Seam, Pit, Contractor, Quantity, Quality, Destination, Equipment, Shift.

System dapat melakukan reconciliation antara Mining Quantity, Survey Quantity, Weighbridge Quantity, dan Stockpile Quantity.

# 13. HAULING MANAGEMENT

System menyimpan Origin, Destination, Route, Distance, Material, Equipment, Trip, Quantity.

Commercial quantity dapat menggunakan Ton × Distance atau BCM × Distance, tergantung kontrak.

# 14. SURVEY & MEASUREMENT

Survey merupakan fungsi critical karena menjadi dasar commercial quantity.

Data: Survey Date, Survey Period, Pit, Block, Contractor, Material, Beginning Volume, Ending Volume, Difference, Survey Quantity.

Workflow: Survey Measurement → Survey Verification → Engineering Review → Operation Confirmation → Final Quantity.

Final quantity dikunci setelah approval.

# 15. PRODUCTION RECONCILIATION

System membandingkan Contractor DPR, Owner Operation, Survey, dan Commercial Approved Quantity.

System menghitung variance secara otomatis. Tolerance dapat dikonfigurasi, misalnya ±2%.

Jika melebihi tolerance: Exception → Investigation → Resolution → Approval.

# 16. FUEL MANAGEMENT

Fuel Transaction: Date, Equipment, Contractor, Fuel Station, Liter, Hour Meter, Operator, Fuel Truck, Transaction Reference.

Fuel KPI:

Fuel Ratio = Liter / BCM

Fuel Ratio = Liter / Ton

Fuel Efficiency = Liter / Operating Hour

System membandingkan Standard Fuel Ratio vs Actual Fuel Ratio dan menghasilkan alert jika melewati threshold.

# 17. CONTRACTOR PERFORMANCE MANAGEMENT

Contractor Scorecard dapat menggunakan kategori dan bobot contoh: Production 30%, Equipment 15%, Productivity 15%, Fuel 10%, HSE 15%, Quality 5%, Compliance 10%.

Final Score = Σ (KPI Achievement × KPI Weight)

Output: Contractor Ranking, Monthly Score, Trend, KPI Detail, Underperformance Alert.

# 18. HSE PERFORMANCE

Data: Fatality, LTI, Medical Treatment, First Aid, Near Miss, Property Damage, Environmental Incident, Safety Observation, Inspection, Safety Compliance.

KPI: LTIFR, TRIFR, Incident Rate, Safety Compliance, Inspection Compliance.

HSE score dapat menjadi bagian dari contractor performance.

# 19. CONTRACT PROGRESS

Original Contract Value + Amendment = Revised Contract Value.

Revised Contract Value - Previous Claims - Current Claim = Remaining Contract.

Dashboard: Contract Value, Utilized Value, Remaining Value, Utilization %, Contract Expiry, Forecast Completion.

Alert: Contract >80% utilized, Contract >90% utilized, Contract expiring, Quantity exceeding contract.

# 20. PROGRESS CLAIM

Contractor dapat membuat progress claim berdasarkan quantity yang telah approved.

System mengambil otomatis Approved Quantity, Contract Rate, Distance, Adjustment, Penalty, Incentive.

Gross Claim = Approved Quantity × Contract Rate.

Net Claim = Gross Claim + Incentive - Penalty - Deduction.

# 21. BILLING VERIFICATION

Workflow: Contractor Claim → Operation Verification → Survey Verification → Engineering Verification → Commercial Verification → Mine Manager Approval → Finance → Invoice → Payment.

System harus mencegah invoice apabila quantity belum approved.

# 22. PENALTY & INCENTIVE

Rule dapat dikonfigurasi berdasarkan contract.

Penalty: Production below target, Equipment availability below SLA, Excessive fuel consumption, Safety violation, Quality deviation, Environmental violation.

Incentive: Production above target, Productivity improvement, Fuel efficiency, Zero incident, Cost reduction.

Calculation engine harus configurable tanpa perubahan source code.

# 23. COST MANAGEMENT

System menghitung cost berdasarkan Contractor, Pit, Activity, Equipment, dan Period.

KPI:

OB Cost = Total OB Cost / BCM

Coal Mining Cost = Mining Cost / Ton

Hauling Cost = Hauling Cost / Ton

Management dapat melihat Budget → Forecast → Actual → Variance.

# 24. MANAGEMENT DASHBOARD

Executive Dashboard minimal menampilkan:

Production: Coal Plan, Coal Actual, Achievement, OB Plan, OB Actual, Stripping Ratio.

Contractor: Contractor Ranking, Production Achievement, Equipment Availability, Productivity, Fuel Efficiency, HSE Score.

Cost: Mining Cost/Ton, OB Cost/BCM, Hauling Cost/Ton, Budget vs Actual.

Contract: Contract Value, Utilization, Remaining Value, Expiring Contract.

Exception: Production below target, Fuel anomaly, Equipment underperformance, Quantity discrepancy, Contract over-utilization, Safety incident.

# 25. OPERATION CONTROL TOWER

System disarankan memiliki Mining Operation Control Tower yang menampilkan ringkasan Coal Production, Overburden, Contractor Performance, Equipment Status, serta operational alerts dalam satu layar untuk management.

# 26. ALERT & NOTIFICATION

Configurable alert:

Production <90% target: Production Warning

PA <85%: Equipment Alert

Fuel > standard +10%: Fuel Alert

Contract utilization >80%: Contract Warning

Contract expiry <90 days: Contract Expiry

Survey variance >2%: Quantity Alert

HSE incident: Critical HSE Alert

Notification melalui in-system notification, email, API/integration, dan mobile notification pada fase berikutnya.

# 27. DOCUMENT MANAGEMENT

Dokumen dapat dilampirkan pada Contract, Amendment, Daily Report, Survey Report, Production Reconciliation, Progress Claim, Invoice, HSE Report, dan Supporting Evidence.

System menyimpan Document Type, File, Version, Uploaded By, Uploaded Date, Reference Transaction.

# 28. WORKFLOW ENGINE

Workflow harus configurable.

Standard status: DRAFT → SUBMITTED → VERIFIED → APPROVED → CLOSED.

Alternatif: REJECTED, RETURN FOR REVISION, CANCELLED.

Setiap approval menyimpan Approver, Date, Decision, Comment, Previous Status, New Status.

# 29. AUDIT TRAIL

Setiap transaksi harus mencatat Created By, Created Date, Modified By, Modified Date, Approved By, Approved Date.

Perubahan critical data harus menyimpan Old Value, New Value, Changed By, Changed Date, Reason.

Approved transaction tidak boleh diedit langsung. Correction harus melalui controlled revision/reopen process.

# 30. INTEGRATION REQUIREMENTS

Architecture harus menyediakan REST API untuk integrasi dengan ERP/Odoo/SAP, Weighbridge, GPS/Fleet Management System, Fuel Management System, Laboratory/Coal Quality, HR System, Procurement System, Finance System, dan Document Management System.

# 31. DATA IMPORT

Untuk tahap awal implementasi, sistem harus mendukung Excel/CSV import untuk Production, Equipment, Fuel, Survey, Contract, Rate, Target, HSE, dan Historical production.

Proses import: Upload → Data Validation → Preview → Error Identification → Confirmation → Posting.

# 32. MOBILE / FIELD OPERATION

System harus responsive untuk Desktop, Tablet, dan Mobile Browser.

Field user harus dapat melakukan Daily activity input, Equipment status update, Production input, Fuel input, Photo attachment, Approval, dan Issue reporting.

Future enhancement dapat menggunakan dedicated mobile application.

# 33. NON-FUNCTIONAL REQUIREMENTS

Performance: standard transaction response <3 seconds; dashboard <5 seconds; heavy analytics dapat menggunakan asynchronous processing.

Availability target minimum: 99.5%.

Security minimum: HTTPS, password encryption, RBAC, session timeout, audit log, API authentication, file access authorization, database backup.

Scalability: multiple sites, multiple contractors, multiple contracts, millions of production transactions, historical analytics.

# 34. CORE DATA MODEL

Core entities: COMPANY, SITE, PIT, BLOCK, SEAM, CONTRACTOR, CONTRACT, CONTRACT_RATE, EQUIPMENT, EQUIPMENT_STATUS, MINING_PLAN, PRODUCTION_TARGET, DAILY_OPERATION, PRODUCTION, HAULING, FUEL_TRANSACTION, SURVEY, RECONCILIATION, CONTRACTOR_KPI, CONTRACTOR_SCORE, PROGRESS_CLAIM, CLAIM_DETAIL, PENALTY, INCENTIVE, INVOICE, HSE_INCIDENT, DOCUMENT, WORKFLOW, APPROVAL, USER, ROLE, AUDIT_LOG.

Relationship utama: CONTRACTOR → CONTRACT → CONTRACT_RATE; CONTRACTOR → EQUIPMENT; CONTRACTOR → PRODUCTION; CONTRACTOR → FUEL; CONTRACTOR → KPI; CONTRACTOR → PROGRESS_CLAIM.

# 35. KEY BUSINESS CONTROLS

BR-001 Production quantity yang belum diverifikasi tidak boleh digunakan untuk billing.

BR-002 Survey quantity yang telah final tidak dapat diubah tanpa reopening approval.

BR-003 Rate billing harus berasal dari active contract rate.

BR-004 Contractor tidak dapat mengakses transaksi contractor lain.

BR-005 Invoice tidak dapat melebihi approved progress claim.

BR-006 Claim tidak dapat melebihi remaining contract quantity/value tanpa approval.

BR-007 Duplicate production transaction harus dicegah.

BR-008 Fuel transaction harus memiliki equipment valid.

BR-009 Equipment harus terasosiasi dengan contractor yang valid pada periode transaksi.

BR-010 Penalty dan incentive harus mempunyai calculation evidence.

BR-011 Approved transaction harus immutable dan perubahan dilakukan melalui controlled revision.

# 36. IMPLEMENTATION PHASING

Phase 1 – Mining Operation Control: Master Data, Contractor, Contract, Mining Plan, Daily Production, Equipment, Survey, Reconciliation, Dashboard. Outcome: single source of truth untuk monitoring produksi contractor.

Phase 2 – Contractor Performance & Cost: Fuel, Equipment KPI, Contractor KPI, HSE, Cost Analysis, Penalty & Incentive. Outcome: mengukur produktivitas dan efisiensi contractor.

Phase 3 – Commercial & Billing: Contract utilization, Progress claim, Commercial verification, Billing, ERP integration. Outcome: Production → Measurement → Claim → Invoice terintegrasi.

Phase 4 – Intelligent Mining Management: Production forecasting, Fuel anomaly detection, Equipment productivity analytics, Contractor performance prediction, Cost forecasting, Automated management insights, Natural-language analytics.

# 37. TARGET END-STATE

Target platform mengintegrasikan Management/Executive Dashboard, Mining Control Tower, Planning, Operation, Commercial, Survey/Reconciliation, Contractor KPI, Cost Analytics, dan Insight Engine.

MCMS diposisikan sebagai Owner Mining Management Platform yang menghubungkan operational, technical, contractor performance, commercial, dan financial dalam satu data model.

# 38. KEY SUCCESS INDICATORS

≥95% daily production captured digitally

≥95% equipment activity captured

100% contractor claims linked dengan verified quantity

100% contract rates maintained centrally

Reduction of manual reconciliation

Reduction of billing disputes

Visibility of cost per BCM/Ton

Contractor performance score tersedia setiap bulan

Contract utilization dapat dimonitor secara real-time

Management dashboard menjadi single source of truth

Full audit trail untuk production-to-payment process

# 39. RECOMMENDED SYSTEM POSITIONING

Nama yang disarankan: Integrated Mining Contractor Management System (iMCMS) atau Mining Operations & Contractor Performance Management System.

System positioning:

“An integrated owner-side platform to control mining production, contractor performance, operational cost, contract utilization, and payment validation from plan to payment.”